## Sheet1
CODAPS - PEP Companion App Required Features Document
Required | Status | Comments
Bilingual | Mostly Complete | We are missing official translations for some of the entries.
Save User Profile | Complete
Voluntary Incident Report Form | Complete
Compliance Violation Report Form | Complete
XML File Submission | Complete* | App submits to our test server. Small changes are required to submit to PMRA.
History | Complete
Save forms in Drafts | Complete
Instructions | Complete* | We have implemented all that we could. Further instructions required from the client to be implemented.
Help | Complete | Complete and operational in both official languages.
Preferred
Reading Room Request Form | Complete (To best ability) | Client hasn't finalized this form, so it is implemented as best as we were able.
Notice of Objection | Complete (To best ability) | Client hasn't finalized this form, so it is implemented as best as we were able.
Consultation Comment | Complete (To best ability) | Client hasn't finalized this form, so it is implemented as best as we were able.
Information Service Inquiry Form | Complete (To best ability) | Client hasn't finalized this form, so it is implemented as best as we were able.
Base 64 Image Submission | Complete
File Attachments | Not complete | Insufficient time.
Desired
Geocoded GPS Location | Complete | Is enabled in the permissions